## Task_Table
ID | Task | Assigned to | Duration (days) | Start | Finish | Notes
Initial Documentation | [5 empty] | Schedules to be adjusted depending on setbacks / availability of each developer
1 | Scope document | Diego, Gerardo | 18 | 2020-08-17 10:30 | 2020-09-04
2 | SRS (Software Requirements Specification) | Diego, Gerardo | 14 | 2020-08-21 | 2020-09-04
3 | Adjust project scope after client feedback | Diego, Gerardo | 0 | 2020-09-04 | 2020-09-04
4 | Implementation plan (this document) | Diego, Gerardo | 16 | 2020-08-19 | 2020-09-04
5 | Prioritisation of requirements based on SRS (Moscow) | Diego, Gerardo | 7 | 2020-08-28 | 2020-09-04
6 | Adjust UI design after client feedback | Diego, Gerardo | 3 | 2020-09-04 | 2020-09-07
7 | Test plan | Diego, Gerardo | 13 | 2020-08-22 | 2020-09-04
8 | Report document (weekly) | Diego, Gerardo | 110 | 2020-08-21 | 2020-12-09 | Weekly reports will be provided until the project is delivered
Development Phase
9 | Analyse requirements | Diego, Gerardo | 3 | 2020-09-04 | 2020-09-07
| Validate requirements with clients | Diego, Gerardo | 3 | 2020-09-07 | 2020-09-10
10 | Research Hair style script | Diego, Gerardo | 7 | 2020-09-07 | 2020-09-14
12 | Upskilling: FastAPI | Diego, Gerardo | 5 | 2020-09-07 | 2020-09-12
13 | Upskilling: Dart and Flutter | Diego, Gerardo | 5 | 2020-09-14 | 2020-09-19
14 | Upskilling: AWS (EC2, S3, Route53, RDS) | Diego, Gerardo | 5 | 2020-09-14 | 2020-09-19
15 | Design Python API | Gerardo | 7 | 2020-09-21 | 2020-09-28
16 | Migrate project from Digital Ocean to AWS | Diego, Gerardo | 5 | 2020-08-24 | 2020-08-29
17 | Implement Python API | Diego, Gerardo | 13 | 2020-09-22 | 2020-10-05
18 | Secure API | Diego, Gerardo | 8 | 2020-10-05 | 2020-10-13
19 | Test Python API | Diego | 8 | 2020-10-05 | 2020-10-13
20 | Design App | Diego, Gerardo | 5 | 2020-10-05 | 2020-10-10
21 | Implement Flutter app | Diego, Gerardo | 14 | 2020-10-12 | 2020-10-26
22 | Validate data | Diego, Gerardo | 5 | 2020-10-12 | 2020-10-17
23 | Write unit tests | Diego, Gerardo | 8 | 2020-10-05 | 2020-10-13
24 | Move code to cloud environment (AWS) | Diego, Gerardo | 14 | 2020-10-24 | 2020-11-07
25 | White box testing | Diego, Gerardo | 8 | 2020-10-05 | 2020-10-13
26 | Black box testing | Diego, Gerardo | 4 | 2020-10-13 | 2020-10-17
27 | Performance metrics | Diego, Gerardo | 5 | 2020-10-19 | 2020-10-24
Deployment Phase
29 | Implement logging | Diego | 6 | 2020-10-19 | 2020-10-25
30 | Present prototype to clients | Diego, Gerardo | 7 | 2020-10-17 | 2020-10-24
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
Formulas:
Duration (days) = DAYS([Finish], [Start])

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Management | M | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Analyst | A | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Developer | D | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Testers | T | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Trainers | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Technical Communicators | T | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Deployment Team | D | Work |  |  |  |  | 100% | $0.00/h | 0