## Task_Table
ID | Task | Assigned to | Duration (days) | Start | Finish | Notes
Initial Documentation | [5 empty] | Schedules to be adjusted depending on setbacks / availability of each developer
1 | Scope document | Diego, Gerardo | 18 | 2020-08-17 10:30 | 2020-09-04
2 | SRS (Software Requirements Specification) | Diego, Gerardo | 14 | 2020-08-21 | 2020-09-04
3 | Adjust project scope after client feedback | Diego, Gerardo | 0 | 2020-09-04 | 2020-09-04
4 | Implementation plan (this document) | Diego, Gerardo | 16 | 2020-08-19 | 2020-09-04
5 | Prioritisation of requirements based on SRS (Moscow) | Diego, Gerardo | 7 | 2020-08-28 | 2020-09-04
6 | Adjust UI design after client feedback | Diego, Gerardo | 3 | 2020-09-04 | 2020-09-07
7 | Test plan | Diego, Gerardo | 13 | 2020-08-22 | 2020-09-04
8 | Report document (weekly) | Diego, Gerardo | 110 | 2020-08-21 | 2020-12-09 | Weekly reports will be provided until the project is delivered
Development Phase
9 | Analyse requirements | Diego, Gerardo | 3 | 2020-09-04 | 2020-09-07
10 | Research Hair style script | Diego, Gerardo | 7 | 2020-09-07 | 2020-09-14
11 | Upskilling: FastAPI | Diego, Gerardo | 5 | 2020-09-07 | 2020-09-12
12 | Upskilling: Dart and Flutter | Diego, Gerardo | 5 | 2020-09-14 | 2020-09-19
13 | Upskilling: Docker and CI/CD | Diego, Gerardo | 5 | 2020-09-14 | 2020-09-19
14 | Upskilling: AWS (EC2, S3, Route53, RDS) | Diego, Gerardo | 5 | 2020-09-14 | 2020-09-19
15 | Design Python API | Gerardo | 7 | 2020-09-21 | 2020-09-28
16 | Migrate project from Digital Ocean to AWS | Diego, Gerardo | 5 | 2020-08-24 | 2020-08-29
17 | Implement Python API | Diego, Gerardo | 13 | 2020-09-22 | 2020-10-05
18 | Secure API | Diego, Gerardo | 8 | 2020-10-05 | 2020-10-13
19 | Test Python API | Diego | 8 | 2020-10-05 | 2020-10-13
20 | Design App | Diego, Gerardo | 5 | 2020-10-05 | 2020-10-10
21 | Implement Flutter app | Diego, Gerardo | 14 | 2020-10-12 | 2020-10-26
22 | Validate data | Diego, Gerardo | 5 | 2020-10-12 | 2020-10-17
23 | Write unit tests | Diego, Gerardo | 8 | 2020-10-05 | 2020-10-13
24 | White box testing | Diego, Gerardo | 8 | 2020-10-05 | 2020-10-13
25 | Black box testing | Diego, Gerardo | 4 | 2020-10-13 | 2020-10-17
26 | Performance metrics | Diego, Gerardo | 5 | 2020-10-19 | 2020-10-24
27 | Validate requirements with clients | Diego, Gerardo | 7 | 2020-10-26 | 2020-11-02
28 | Make final changes based on client's feedback (if needed) | Diego, Gerardo | 7 | 2020-11-02 | 2020-11-09 | Cut-off period to make changes to the application, developers will deploy it to a live environment afterwards
Deployment Phase
29 | Move code to production environment (AWS) | Diego, Gerardo | 4 | 2020-11-05 | 2020-11-09
30 | Enable and configure required services | Diego, Gerardo | 3 | 2020-11-09 | 2020-11-12
31 | Set up permissions / credentials | Gerardo | 2 | 2020-11-16 | 2020-11-18
32 | Configure SSL / HTTPS | Diego | 2 | 2020-11-16 | 2020-11-18
33 | Implement logging | Diego | 3 | 2020-11-16 | 2020-11-19
34 | Performance metrics (live) | Diego, Gerardo | 2 | 2020-11-18 | 2020-11-20
35 | Deliver the project | Diego, Gerardo | 0 | 2020-11-21 | 2020-11-21 | Coincides with the deadline to submit Assessment 2 for the Advanced OOP cluster
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
Formulas:
Duration (days) = DAYS([Finish], [Start])